## Combined
Subcontractor: | A K Saini Construction
State: | Uttar Pradesh |  | A K Saini Construction |  |  |  |  | Pipe Laying work
District: | Muzaffarnagar
Block: | Muzaffarnagar
PMC_No | Invoice_Details | Invoice_Date | Invoice_No | Basic_Amount | Debit_Amount | After_Debit_Amount | GST_Amount | Amount | TDS_Amount | SD_Amount | On_Commission | Hydro_Testing | GST_SD_Amount | Hold the Amount because the Qty. is more then the DPR | Final_Amount |  | PAYMENT NOTE No. | Total_Amount | UTR
[7 empty] | 18% |  | 1% | 5% | 10% | 10% | 18%
53361
53361 | Sohajani Jatan Village Pipe laying work | 2022-12-12 | 6 | 312091 | 80919 | 231172 | 41611 | 272783 | 2311.72 | 11558.6 | 23117.2 | 23117.2 | 41611 | 9477 | 161590 |  | RIUP22/1620 | 161590 | 26-12-2022 NEFT/AXISP00348647834/RIUP22/1620/A K SAINI CONST 161590.00
53361 | GST release note |  | 6 | 41611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41611 |  | 0 | 0 | 0
53361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
53361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 41611
[6 empty] | 0 | 0% | 0 | 0% | [6 empty] | 51556
51556 | Meghakheri Village Pipe laying work | 2022-10-01 | 4 | 1272181.45 | 139987 | 1132194 | 203795 | 1335989 | 11321.94 | 56609.7 | 56609.7 | 113219.4 | 203795 | 97098 | 797335 |  | RIUP22/928 | 495000 | 10-10-2022 NEFT/AXISP00327017850/RIUP22/928/A K SAINI CONSTR 495000.00
51556 | Meghakheri Village Pipe laying work | 2022-11-14 | 5 | 559849.95 | 33267 | 526583 | 94785 | 621368 | 5265.83 | 26329.15 | 26329.15 | 52658.3 | 94785 | 67409 | 348592 |  | RIUP22/967 | 297000 | 12-10-2022 NEFT/AXISP00327681886/RIUP22/967/A K SAINI CONSTR 297000.00
51556 | GST release note | 0 | 5 | 298580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 298580 |  | RIUP22/1042 | 5335 | 20-10-2022 NEFT/AXISP00330028514/RIUP22/1042/A K SAINI CONST 5335.00
51556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | RIUP22/1241 | 148500 | 14-11-2022 NEFT/AXISP00337247388/RIUP22/1241/A K SAINI CONST 148500.00
51556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | RIUP22/1286 | 200092 | 22-11-2022 NEFT/AXISP00339527007/RIUP22/1286/A K SAINI CONST 200092.00
51556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
51556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
51556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 298580
51555
51555 | Faloda Village Pipe laying work | 2022-08-05 | 3 | 381511.76 | 74016 | 307495.76 | 55349 | 362844.76 | 3074.9576 | 15374.788 | 15374.788 | 30749.576 | 55349 | 0 | 242922 |  | RIUP22/496 | 242921 | 24-08-2022 NEFT/AXISP00314017487/RIUP22/496/A K SAINI CONSTR 242921.00
51555 | GST release note | 0 | 3 | 55349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55349 |  | 0 | 0 | 0
51555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
51555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 55350
[10 empty] | 109872.238 | 121430.838 | 219744.476 | 395540 | 173984 | 1945979 |  | Total Paid | 1550438
[17 empty] | Balance Payable | 395541
A K Saini Construction
Sheetal -08.06.2024
[12 empty] | Hold amount |  | 451047.552
[12 empty] | DPR Excess Hold |  | 173984
[12 empty] | Adv/Surplus |  | 395541
[12 empty] | GST pending |  | 0

## 53361
Muzaffarnagar UP
Invoice Reconcilation |  | Saini Construction |  |  |  |  | Pipe Laying work
Invoice Details | Invoice Date | Invoice No | Basic Amt | Debit | After Debit Amt | 18% GST | Amount | TDS (1%) | SD (5%) | On Commissioning | Hydro Testing | GST SD (18%) | Hold the Amount because the Qty. is more then the DPR | Final Amount | PAYMENT NOTE No. | Total Amount Paid | UTR
[6 empty] | 18% |  | 1% | 5% | 10% | 10% | 18%
Sohajani Jatan Village Pipe laying work | 2022-12-12 | 6 | 312091 | 80919 | 231172 | 41611 | 272783 | 2311.72 | 11558.6 | 23117.2 | 23117.2 | 41611 | 9477 | 161590 | RIUP22/1620 | 161590 | 26-12-2022 NEFT/AXISP00348647834/RIUP22/1620/A K SAINI CONST 161590.00
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
[10 empty] | Total Payable Amount Rs. - |  |  |  | 161590 | Total Paid | 161590
[15 empty] | Balance Payable | 0

## 51556
Muzaffarnagar UP
Invoice Reconcilation |  | A.K. Saini Construction |  |  |  |  | Pipe Laying work
Invoice Details | Invoice Date | Invoice No | Basic Amt | Debit | After Debit Amt | 18% GST | Amount | TDS (1%) | SD (5%) | On Commissioning | Hydro Testing | GST SD (18%) | Hold the Amount because the Qty. is more then the DPR | Final Amount | PAYMENT NOTE No. | Total Amount Paid | UTR
[6 empty] | 18% |  | 1% | 5% | 5% | 10% | 18%
Meghakheri Village Pipe laying work. | 2022-10-01 | 4 | 1272181.45 | 139987 | 1132194 | 203795 | 1335989 | 11321.94 | 56609.7 | 56609.7 | 113219.4 | 203795 | 97098 | 797335 | RIUP22/928 | 495000 | 10-10-2022 NEFT/AXISP00327017850/RIUP22/928/A K SAINI CONSTR 495000.00
Meghakheri Village Pipe laying work. | 2022-11-14 | 5 | 559849.95 | 33267 | 526583 | 94785 | 621368 | 5265.83 | 26329.15 | 26329.15 | 52658.3 | 94785 | 67409 | 348592 | RIUP22/967 | 297000 | 12-10-2022 NEFT/AXISP00327681886/RIUP22/967/A K SAINI CONSTR 297000.00
[5 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0 | RIUP22/1042 | 5335 | 20-10-2022 NEFT/AXISP00330028514/RIUP22/1042/A K SAINI CONST 5335.00
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | RIUP22/1241 | 148500 | 14-11-2022 NEFT/AXISP00337247388/RIUP22/1241/A K SAINI CONST 148500.00
[15 empty] | RIUP22/1286 | 200092 | 22-11-2022 NEFT/AXISP00339527007/RIUP22/1286/A K SAINI CONST 200092.00
[10 empty] | Total Payable Amount Rs. - |  |  |  | 1145927 | Total paid | 1145927
[15 empty] | Balance Payable | 0

## 51555
Muzaffarnagar UP
Invoice Reconcilation |  | A.K. Saini Construction |  |  |  |  | Pipe Laying work
Invoice Details | Invoice Date | Invoice No | Basic Amt | Debit | After Debit Amt | 18% GST | Amount | TDS (1%) | SD (5%) | On Commissioning | Hydro Testing | GST SD (18%) | Hold the Amount because the Qty. is more then the DPR | Final Amount | PAYMENT NOTE No. | Total Amount Paid | UTR
[6 empty] | 18% |  | 1% | 5% | 5% | 5% | 18%
Faloda Village Pipe laying work | 2022-08-05 | 03 | 381511.76 | 74016 | 307495.76 | 55349 | 362844.76 | 3074.9576 | 15374.788 | 15374.788 | 30749.576 | 55349 | 0 | 242922 | RIUP22/496 | 242921 | 24-08-2022 NEFT/AXISP00314017487/RIUP22/496/A K SAINI CONSTR 242921.00
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
[5 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
[12 empty] | Total Payable amount |  | 242922 | Total Paid | 242921
[15 empty] | Balance Payable | 1