## Contractor Report
Contractor Name | A K Saini Construction
State
District
Block
Mobile No
GST Type
GST No
PAN No
Email
Address
PMC No | Village | Work Type | Invoice Details | Invoice Date | Invoice No | Basic Amount | Debit | After Debit Amount | GST (18%) | Amount | TDS (1%) | SD (5%) | On Commission | Hydro Testing | GST SD Amount | Hold the Amount because the Qty. is more then the DPR | Final Amount | Payment Amount | TDS Payment | Total Paid | UTR
53361 | sohajani jatan | pipe laying work | Sohajani Jatan Village Pipe laying work | 2022-12-12 | 6 | 312091 | 80919 | 231172 | 41611 | 272783 | 2311.72 | 11558.6 | 23117.2 | 23117.2 | 41611 | 9477 | 161590 | 0 | 0 | 161590 | 26-12-2022 NEFT/AXISP00348647834/RIUP22/1620/A K SAINI CONST 161590.00
53361 |  |  | GST Release Note |  | 6 | 41611 | [10 empty] | 41611
51556 | meghakheri | pipe laying work | Meghakheri Village Pipe laying work | 2022-10-01 | 4 | 1272181.45 | 139987 | 1132194 | 203795 | 1335989 | 11321.94 | 56609.7 | 56609.7 | 113219.4 | 203795 | 97098 | 797335 | 0 | 0 | 495000 | 10-10-2022 NEFT/AXISP00327017850/RIUP22/928/A K SAINI CONSTR 495000.00
51556 | meghakheri | pipe laying work | Meghakheri Village Pipe laying work | 2022-11-14 | 5 | 559849.95 | 33267 | 526583 | 94785 | 621368 | 5265.83 | 26329.15 | 26329.15 | 52658.3 | 94785 | 67409 | 348592 | 0 | 0 | 297000 | 12-10-2022 NEFT/AXISP00327681886/RIUP22/967/A K SAINI CONSTR 297000.00
51556 |  |  | GST Release Note |  | 5 | 298580 | [10 empty] | 298580 | 0 | 0 | 5335 | 20-10-2022 NEFT/AXISP00330028514/RIUP22/1042/A K SAINI CONST 5335.00
51556 | [17 empty] | 0 | 0 | 148500 | 14-11-2022 NEFT/AXISP00337247388/RIUP22/1241/A K SAINI CONST 148500.00
51556 | [17 empty] | 0 | 0 | 200092 | 22-11-2022 NEFT/AXISP00339527007/RIUP22/1286/A K SAINI CONST 200092.00
51555 | faloda | pipe laying work | Faloda Village Pipe laying work | 2022-08-05 | 3 | 381511.76 | 74016 | 307495.76 | 55349 | 362844.76 | 3074.96 | 15374.79 | 15374.79 | 30749.58 | 55349 | 0 | 242922 | 0 | 0 | 242921 | 24-08-2022 NEFT/AXISP00314017487/RIUP22/496/A K SAINI CONSTR 242921.00
51555 |  |  | GST Release Note |  | 3 | 55349 | [10 empty] | 55349
51990 | kelashikarpur | oht 200kl 14 mtr work | Kelashikarpur Village OHT 200Kl 14 mtr work | 2023-02-13 | 11 | 1336500 | 881692.7 | 454807 | 81865 | 536672 | 4548 | 22740 | 0 | 0 | 81865 |  | 382038 | 0 | 200000 | 198000 | 28-06-2023 NEFT/AXISP00401570071/RIUP23/944/JANARDAN ORGANIC ₹ 1,98,000.00
51990 |  |  | GST Release Note |  | 11 | 81865 | [10 empty] | 81865 | 0 | 400000 | 396000 | 19-08-2022 NEFT/AXISP00312898798/RIUP22/537/JANARDAN ORGANIC 396000.00
51990 | kelashikarpur | oht 200kl 14 mtr work | Kelashikarpur Village OHT 200Kl 14 mtr work | 2023-04-15 | 2 | 123750 | 0 | 123750 | 22275 | 146025 | 1238 | 6188 | 0 | 0 | 22275 |  | 103949 | 0 | 600000 | 594000 | 28-10-2022 NEFT/AXISP00332142997/RIUP22/1123/JANARDAN ORGANI 594000.00
51990 |  |  | GST Release Note |  | 2 | 22275 | [10 empty] | 22275 | 0 | 200000 | 198000 | 04-11-2023 NEFT/AXISP00440433098/RIUP23/3065/JANARDAN ORGANIC F/UBIN0565750 198000.00
51990 | kelashikarpur | oht 200kl 14 mtr work | Kelashikarpur Village OHT 200Kl 14 mtr work | 2023-08-09 | 66213 | 6 | 302103 | -302097 | -54377.46 | -356474.46 | -3020.97 | -15104.85 |  | 0 | -54377.46 |  | -283971 | 0 | 400000 | 396000 | 27-09-2024 NEFT/AXISP00544997299/RIUP24/1951/JANARDAN ORGANICF/UBIN0565750 396000.00
51990 | kelashikarpur | oht 200kl 14 mtr work | Kelashikarpur Village OHT 200Kl 14 mtr work | 2023-08-10 | 56204 | 162250 | 0 | 162250 | 29205 | 191455 | 1622.5 | 8112.5 |  | 0 | 29205 |  | 152515 | 0 | 500000 | 495000 | 30-10-2024 NEFT/AXISP00561828557/RIUPP24/2383/JANARDAN ORGANICF/UBIN0565750 495000.00
51990 | kelashikarpur | oht 200kl 14 mtr work | Kelashikarpur Village OHT 200Kl 14 mtr work | 2023-09-13 | 83228 | 147500 | 88925 | 58575 | 10543.5 | 69118.5 | 585.75 | 2928.75 |  | 0 | 10543.5 |  | 49203 | 0 | 500000 | 495000 | 28-11-2024 NEFT/AXISP00575677758/RIUP24/2528/JANARDAN ORGANICF/UBIN0565750 495000.000
51990 | [17 empty] | 0 | 500000 | 495000 | 05-12-2024 NEFT/AXISP00580318074/RIUP24/2585/JANARDAN ORGANICF/UBIN0565750 495000.00
52402 | kheri khushnam | oht construction work | Kheri Khushnam Village OHT Construction work | 2023-12-19 | 4 | 920000 | 336997 | 583003 | 104941 | 687944 | 5830 | 29150 | 0 | 0 | 104941 |  | 489723 | 0 | 300000 | 297000 | 20-09-2022 NEFT/AXISP00321260567/RIUP22/784/JANARDAN ORGANIC ₹ 2,97,000.00
52402 |  |  | GST Release Note |  | 4 | 104941 | [10 empty] | 104941 | 0 | 300000 | 297000 | 07-09-2022 NEFT/AXISP00318202764/RIUP22/697/JANARDAN ORGANIC 297000.00
52402 | kheri khushnam | oht construction work | Kheri Khushnam Village OHT Construction work | 2023-04-15 | 7 | 111792 | 0 | 111792 | 20123 | 131915 | 1118 | 5590 | 0 | 0 | 20123 |  | 93905 | 0 | 100000 | 99000 | 2023 April 07 ------------ Janardan Organic Food Mill ---------- Rs. 1,00,000 ------------ AXISP00379707432
52402 |  |  | GST Release Note |  | 7 | 20123 | [10 empty] | 20123 | 0 | 200000 | 198000 | 04-11-2023 NEFT/AXISP00440433097/RIUP23/3066/JANARDAN ORGANIC F/UBIN0565750 198000.00
52402 | kheri khushnam | oht construction work | Kheri Khushnam Village OHT Construction work | 2023-08-04 | 57205 | 108208 |  | 108208 | 19477 | 127685 | 1082 | 5410 | 0 | 0 | 19477 |  | 101716 | 0 | 200000 | 198000 | 28-06-2023 NEFT/AXISP00401570070/RIUP23/943/JANARDAN ORGANIC ₹ 1,98,000.00
52402 |  |  | GST Release Note |  | 57205 | 19477 | [10 empty] | 19477 | 0 | 1000000 | 990000 | 17-08-2024 NEFT/AXISP00529471070/RIUP24/1483/JANARDAN ORGANIC F/UBIN0565750 ₹ 9,90,000.00
52402 | [17 empty] | 0 | 200000 | 198000 | 27-09-2024 NEFT/AXISP00544997300/RIUP24/1952/JANARDAN ORGANICF/UBIN0565750 198000.00
52402 | [17 empty] | 0 | 500000 | 495000 | 03-12-2024 NEFT/AXISP00579206616/RIUP24/2583/JANARDAN ORGANICF/UBIN0565750 495000.00
52403 | gangarampur | 250 kl 12m oht construction work | Gangarampur Village 250 kl 12m OHT Construction work | 2023-01-29 | 10 | 1088800 | 424798.95 | 664001 | 119520 | 783521 | 6640 | 33200 | 0 | 0 | 119520 |  | 557761 | 0 | 300000 | 297000 | 07-09-2022 NEFT/AXISP00318202763/RIUP22/698/JANARDAN ORGANIC 297000.00
52403 |  |  | GST Release Note |  | 10 | 119520 | [10 empty] | 119520 | 0 | 300000 | 297000 | 20-09-2022 NEFT/AXISP00321260568/RIUP22/785/JANARDAN ORGANIC ₹ 2,97,000.00
52403 | gangarampur | 250 kl 12m oht construction work | Gangarampur Village 250 kl 12m OHT Construction work | 2023-04-15 | 3 | 150125.6 | 0 | 150126 | 27023 | 177149 | 1501 | 7506 | 0 | 0 | 27023 |  | 126106 | 0 | 150000 | 148500 | 20-12-2022 NEFT/AXISP00347623938/RIUP22/1579/JANARDAN ORGANI 148500.00
52403 |  |  | GST Release Note |  | 3 | 27023 | [10 empty] | 27023 | 0 | 50000 | 50000 | 2023 April 07 ---------- Janardam Organic Food Mill ----------- Rs. 50,000 ------------ /AXISP00379707430
52403 | gangarampur | 250 kl 12m oht construction work | Gangarampur Village 250 kl 12m OHT Construction work | 2023-08-04 | 54202 | 550873 | 424799 | 126074 | 22693 | 148767 | 1261 | 6304 | 0 | 0 | 22693 |  | 105902 | 0 | 500000 | 495000 | 18-08-2023 NEFT/AXISP00416756581/RIUP23/1618/JANARDAN ORGANI 495000.00
52403 |  |  | GST Release Note |  | 54202 | 22693 | [10 empty] | 22693 | 0 | 200000 | 198000 | 25-07-2023 NEFT/AXISP00409456856/RIUP23/1209/JANARDAN FOOD ORG 1,98,000.00
52403 | [17 empty] | 0 | 500000 | 495000 | 14-08-2024 NEFT/AXISP00528230422/RIUP24/1437/JANARDAN ORGANIC F/UBIN0565750 495000.00
52403 | [17 empty] | 0 | 500000 | 495000 | 06-09-2024 NEFT/AXISP00537295297/RIUP24/1670/JANARDAN ORGANICF/UBIN0565750 495000.00
52403 | [17 empty] | 0 | 200000 | 198000 | 27-09-2024 NEFT/AXISP00544997301/RIUP24/1953/JANARDAN ORGANICF/UBIN0565750 198000.00
52403 | [17 empty] | 0 | 500000 | 495000 | 21-11-2024 NEFT/AXISP00572732448/RIUP24/2530/JANARDAN ORGANICF/UBIN0565750 495000.00
52629 | makheri kadargarh | oht construction work | Makheri kadargarh Village OHT Construction work | 2023-01-20 | 8 | 1164000 | 506542 | 657458 | 118342 | 775800 | 6575 | 32873 | 0 | 0 | 118342 |  | 552264 | 0 | 600000 | 594000 | 28-10-2022 NEFT/AXISP00332142998/RIUP22/1124/JANARDAN ORGANI 594000.00
52629 |  |  | GST Release Note |  | 8 | 118342.46 | [10 empty] | 118342.46 | 0 | 500000 | 495000 | 24-01-2023 NEFT/AXISP00330179787/RIUP22/1996/JANARDAN ORGANI 495000.00
52629 | makheri kadargarh | oht construction work | Makheri kadargarh Village OHT Construction work | 2023-04-15 | 4 | 188718.4 |  | 188718 | 33969 | 222687 | 1887 | 9436 | 0 | 0 | 33969 |  | 158523 | 0 | 250000 | 247500 | 30-06-2023 NEFT/AXISP00402152394/RIUP23/963/JANARDAN ORGANIC 247500.00
52629 |  |  | GST Release Note |  | 4 | 33969 | [10 empty] | 33969 | 0 | 500000 | 495000 | 06-09-2024 NEFT/AXISP00537295298/RIUP24/1671/JANARDAN ORGANICF/UBIN0565750 495000.00
52629 | makheri kadargarh | oht construction work | Makheri kadargarh Village OHT Construction work | 2023-08-04 | 58206 | 652724.65 | 535443.05 | 117282 | 21111 | 138393 | 1173 | 5864 |  | 0 | 21111 |  | 110245 | 0 | 500000 | 495000 | 14-08-2024 NEFT/AXISP00528230423/RIUP24/1438/JANARDAN ORGANIC F/UBIN0565750 495000.00
52629 | [17 empty] | 0 | 500000 | 495000 | 20-12-2024 NEFT/AXISP00587058625/RIUP24/2718/JANARDAN ORGANICF/UBIN0565750 495000.00
52629 | [17 empty] | 0 | 300000 | 297000 | 23-12-2024 NEFT/AXISP00587800976/RIUP24/2674/JANARDAN ORGANICF/UBIN0565750 297000.00
52629 | [17 empty] | 0 | 600000 | 594000 | 26-12-2024 Debit N/RIUP24/2765/JANARDAN ORGAN/INDBN26123786920 594000.0
52523 | titayli | oht construction work | Titayli Village OHT Construction work | 2022-12-09 | 3 | 674500 | 223474 | 451026 | 81185 | 532211 | 4510 | 22551 | 0 | 0 | 81185 |  | 378862 | 0 | 200000 | 198000 | 28-06-2023 NEFT/AXISP00401570069/RIUP23/942/JANARDAN ORGANIC ₹ 1,98,000.00
52523 |  |  | GST Release Note |  | 3 | 81185 | [10 empty] | 81185 | 0 | 300000 | 297000 | 20-09-2022 NEFT/AXISP00321260566/RIUP22/786/JANARDAN ORGANIC ₹ 2,97,000.00
52523 | titayli | oht construction work | Titayli Village OHT Construction work | 2023-04-15 | 8 | 75124 | 0 | 75124 | 13522 | 88646 | 751 | 3756 | 0 | 0 | 13522 |  | 63105 | 0 | 200000 | 198000 | 14-11-2022 NEFT/AXISP00337247391/RIUP22/1251/JANARDAN ORGANI 198000.00
52523 |  |  | GST Release Note |  | 8 | 13522 | [10 empty] | 13522 | 0 | 100000 | 99000 | 18-07-2023 NEFT/AXISP00407734315/RIUP23/1137/JANARDAN ORGANI 99000.00
52523 | titayli | oht construction work | Titayli Village OHT Construction work | 2023-08-04 | 60208 | 270099 | 223473 | 46626 | 8393 | 55019 | 466 | 2331 | 0 | 0 | 8393 |  | 43829 | 0 | 100000 | 99000 | 03-07-2023 NEFT/AXISP00403218877/RIUP23/992/JANARDAN ORGANIC 99000.00
52523 |  |  | GST Release Note |  | 60208 | 8393 | [10 empty] | 8393 | 0 | 200000 | 198000 | 28-07-2023 NEFT/AXISP00410084840/RIUP23/1267A/JANARDAN ORGAN 198000.00
52523 | [17 empty] | 0 | 300000 | 297000 | 27-09-2024 NEFT/AXISP00544997302/RIUP24/1954/JANARDAN ORGANICF/UBIN0565750 297000.00
52523 | [17 empty] | 0 | 500000 | 495000 | 16-11-2024 NEFT/AXISP00570981026/RIUP24/2518/JANARDAN ORGANICF/UBIN0565750 495000.00
52523 | [17 empty] | 0 | 500000 | 495000 | 29-11-2024 NEFT/AXISP00576725432/RIUP24/2491/JANARDAN ORGANIC F/UBIN0565750 495000.00
52630 | mantmanti | 375 kl 12 m staging ht oht construction work | Mantmanti Village 375 KL 12 M staging Ht OHT Construction work | 2023-12-19 | 7 | 1400000 | 540666 | 859334 | 154680 | 1014014 | 8593 | 42967 | 0 | 0 | 154680 |  | 721841 | 0 | 600000 | 594000 | 20-10-2022 NEFT/AXISP00330179783/RIUP22/1050/JANARDAN ORGANI 594000.00
52630 |  |  | GST Release Note |  | 7 | 154680 | [10 empty] | 154680 | 0 | 50000 | 50000 | 2023 April 07 ----------- Janardan Organic Food Mill --------- Rs. 50,000 ------------ /AXISP00379707431
52630 | mantmanti | 375 kl 12 m staging ht oht construction work | Mantmanti Village 375 KL 12 M staging Ht OHT Construction work | 2023-04-15 | 5 | 322888.8 | 0 | 322889 | 58120 | 381009 | 3229 | 16144 | 0 | 0 | 58120 |  | 271227 | 0 | 500000 | 495000 | 24-01-2023 NEFT/AXISP00330179786/RIUP22/1995/JANARDAN ORGANI 495000.00
52630 |  |  | GST Release Note |  | 5 | 58120 | [10 empty] | 58120 | 0 | 500000 | 495000 | 21-08-2024 NEFT/AXISP00530601965/RIUP24/1485/JANARDAN ORGANIC F/UBIN0565750 495000.00
52630 | mantmanti | 375 kl 12 m staging ht oht construction work | Mantmanti Village 375 KL 12 M staging Ht OHT Construction work | 2023-08-04 | 59, 207 | 587777 | 540666 | 47111 | 8480 | 55591 | 471 | 2356 | 0 | 0 | 8480 |  | 44284 | 0 | 500000 | 495000 | 06-09-2024 NEFT/AXISP00537295300/RIUP24/1673/JANARDAN ORGANICF/UBIN0565750 495000.00
52630 |  |  | GST Release Note |  | 59, 207 | 8480 | [10 empty] | 8480 | 0 | 200000 | 198000 | 30-06-2023 NEFT/AXISP00402152395/RIUP23/964/JANARDAN ORGANIC 198000.00
52630 | [17 empty] | 0 | 500000 | 495000 | 30-10-2024 NEFT/AXISP00561828556/RIUPP24/2382/JANARDAN ORGANICF/UBIN0565750 495000.00
52630 | [17 empty] | 0 | 500000 | 495000 | 21-11-2024 NEFT/AXISP00572732447/RIUP24/2529/JANARDAN ORGANICF/UBIN0565750 495000.00
52630 | [17 empty] | 0 | 700000 | 693000 | 22-11-2024 NEFT/AXISP00573604259/RIUP24/2487/JANARDAN ORGANIC F/UBIN0565750 693000.00
52630 | [17 empty] | 0 | 500000 | 495000 | 22-11-2024 NEFT/AXISP00573604258/RIUP24/2517/JANARDAN ORGANIC F/UBIN0565750 495000.00
52631 | badhev kannukheda | oht construction work | Badhev Kannukheda Village OHT Construction work | 2022-12-09 | 2 | 728000 | 255338.02 | 472662 | 85079 | 557741 | 4727 | 23633 | 0 | 0 | 85079 |  | 397036 | 0 | 300000 | 297000 | 14-11-2022 NEFT/AXISP00337247390/RIUP22/1250/JANARDAN ORGANI 297000.00
52631 |  |  | GST Release Note |  | 2 | 85079 | [10 empty] | 85079 | 0 | 200000 | 198000 | 23-12-2022 NEFT/AXISP00348462541/RIUP22/1616/JANARDAN ORGANI 198000.00
52631 | badhev kannukheda | oht construction work | Badhev Kannukheda Village OHT Construction work | 2023-01-29 | 9 | 728000 | 221963.5 | 506037 | 91087 | 597124 | 5060 | 25302 | 0 | 0 | 91087 |  | 425071 | 0 | 300000 | 297000 | 24-11-2022 NEFT/AXISP00340040190/RIUP22/1344/JANARDAN ORGANI 297000.00
52631 |  |  | GST Release Note |  | 9 | 44051 | [10 empty] | 44051 | 0 | 30106 | 30106 | 13-02-2023 NEFT/AXISP00362757393/RIUP22/2142/JANARDAN ORGANI ₹ 30,106.00
52631 |  |  |  |  | 9 | [12 empty] | 0 | 85079 | 85079 | 16-02-2023 NEFT/AXISP00363866679/RIUP22/2183/JANARDAN ORGANI ₹ 85,079.00
52631 |  |  |  |  | 9 | [12 empty] | 0 | 200000 | 198000 | 2023 April 07 ------------ Janardan Organic Food Mills ------------ Rs. 2,00,000 -------------- AXISP00379707434
52631 | [17 empty] | 0 | 7573 | 7573 | 21-04-2023 NEFT/AXISP00383377297/SPUP23/0191/JANARDAN ORGANI 7573.00
52631 | [17 empty] | 0 | 150000 | 148500 | 19-05-2023 NEFT/AXISP00391394987/RIUP23/331/JANARDAN ORGANIC ₹ 1,48,500.00
52631 | [17 empty] | 0 | 500000 | 495000 | 17-08-2024 NEFT/AXISP00589654789/RIUP24/1486/JANARDAN ORGANIC ₹ 495000.00
52631 | [17 empty] | 0 | 1000000 | 990000 | Approval on Whatsapp Dt.30-08-2024. 30-08-2024 NEFT/AXISP00533733866/RIUP24/1587/JANARDAN ORGANICF/UBIN0565750 990000.00
52631 | [17 empty] | 0 | 500000 | 495000 | 06-09-2024 NEFT/AXISP00537295301/RIUP24/1674/JANARDAN ORGANICF/UBIN0565750 495000.00
52631 | [17 empty] | 0 | 300000 | 297000 | 27-09-2024 NEFT/AXISP00544997303/RIUP24/1955/JANARDAN ORGANICF/UBIN0565750 297000.00
52631 | [17 empty] | 0 | 500000 | 495000 | 28-11-2024 NEFT/AXISP00575677758/RIUP24/2528/JANARDAN ORGANICF/UBIN0565750 495000.00
52631 | [17 empty] | 0 | 300000 | 297000 | 28-11-2024 NEFT/AXISP00575677760/RIUP24/2490/JANARDAN ORGANICF/UBIN0565750 297000.00
52631 | [17 empty] | 0 | 500000 | 495000 | 05-12-2024 NEFT/AXISP00580318073/RIUP24/2584/JANARDAN ORGANICF/UBIN0565750 495000.00
52793 | datera | oht construction work | Datera Village OHT Construction work | 2022-12-19 | 5 | 660000 | 197847 | 462153 | 83188 | 545341 | 4622 | 23108 | 0 | 0 | 83188 |  | 388208 | 0 | 500000 | 495000 | 30-11-2022 NEFT/AXISP00341651972/RIUP22/1390/JANARDAN ORGANI 495000.00
52793 |  |  | GST Release Note |  | 5 | 83188 | [10 empty] | 83188 | 0 | 150000 | 148500 | 20-12-2022 NEFT/AXISP00347623939/RIUP22/1578/JANARDAN ORGANI 148500.00
52793 | datera | oht construction work | Datera Village OHT Construction work | 2023-08-04 | 53201 | 236786.8 | 197847 | 38940 | 7009 | 45949 | 389 | 1947 | 0 | 0 | 7009 |  | 32710 | 0 | 500000 | 495000 | 18-08-2023 NEFT/AXISP00416756585/RIUP23/1617/JANARDAN ORGANI 495000.00
52793 | [17 empty] | 0 | 500000 | 495000 | 02-09-2024 NEFT/AXISP00535241237/RIUP24/1585/JANARDAN ORGANICF/UBIN0565750 495000.00
52793 | [17 empty] | 0 | 400000 | 396000 | 12-11-2024 NEFT/AXISP00568034787/RIUP24/2434/JANARDAN ORGANICF/UBIN0565750 396000.00
52793 | [17 empty] | 0 | 400000 | 396000 | 14-11-2024 NEFT/AXISP00569818227/RIUP24/2451/JANARDAN ORGANICF/UBIN0565750 396000.00
52793 | [17 empty] | 0 | 200000 | 198000 | 28-11-2024 NEFT/AXISP00575677759/RIUP24/2489/JANARDAN ORGANICF/UBIN0565750 198000.00
52794 | grahi hasanpur | 400 kl 14 mtr work | Grahi Hasanpur Village 400 KL 14 mtr work | 2023-12-08 | 1 | 816000 | 301729 | 514271 | 92569 | 606840 | 5143 | 25714 | 0 | 0 | 92569 |  | 431987 | 0 | 500000 | 495000 | 14-12-2022 NEFT/AXISP00346247015/RIUP22/1512/JANARDAN ORGANI 495000.00
52794 |  |  | GST Release Note |  | 1 | 92568.78 | [10 empty] | 92568.78 | 0 | 29556 | 29556 | 15-02-2023 NEFT/AXISP00363307377/RIUP22/2178/JANARDAN ORGANI ₹ 29,556.00 - GST adj
52794 | grahi hasanpur | 400 kl 14 mtr work | Grahi Hasanpur Village 400 KL 14 mtr work | 2023-04-15 | 10 | 112664.8 |  | 112665 | 20280 | 132945 | 1127 | 5633 | 0 | 0 | 20280 |  | 94638 | 0 | 100000 | 100000 | 2023 April 07 ---------- Janardan Organic Food Mill ----------- Rs. 1,00,000 ---------- AXISP00379707433
52794 |  |  | GST Release Note |  | 10 | 20280 | [10 empty] | 20280 | 0 | 200000 | 198000 | 28-07-2023 NEFT/AXISP00410084837/RIUP23/1266/JANARDAN ORGANI 198000.00
52794 | grahi hasanpur | 400 kl 14 mtr work | Grahi Hasanpur Village 400 KL 14 mtr work | 2023-08-04 | 55, 203 | 341065 | 301729 | 39336 | 7080 | 46416 | 393 | 1967 | 0 | 0 | 7080 |  | 33042 | 0 | 200000 | 198000 | 28-06-2023 NEFT/AXISP00401570067/RIUP23/940/JANARDAN ORGANIC ₹ 1,98,000.00
52794 |  |  | GST Release Note |  | 55, 203 | 7080 | [10 empty] | 7080 | 0 | 1000000 | 990000 | 22-08-2024 NEFT/AXISP00531016566/RIUP24/1519/JANARDAN ORGANIC F/UBIN0565750 990000.00
52794 | [17 empty] | 0 | 500000 | 495000 | 02-09-2024 NEFT/AXISP00535241238/RIUP24/1586/JANARDAN ORGANICF/UBIN0565750 495000.00
52794 | [17 empty] | 0 | 300000 | 297000 | 24-09-2024 NEFT/AXISP00543503653/RIUP24/1912/JANARDAN ORGANICF/UBIN0565750 297000.00
52794 | [17 empty] | 0 | 500000 | 495000 | 01-10-2024 NEFT/AXISP00547359349/RIUP24/2027/JANARDAN ORGANICF/UBIN0565750 495000.00
52794 | [17 empty] | 0 | 500000 | 495000 | 30-10-2024 NEFT/AXISP00561828555/RIUPP24/2381/JANARDAN ORGANICF/UBIN0565750 495000.00
52794 | [17 empty] | 0 | 400000 | 396000 | 08-11-2024 NEFT/AXISP00566570856/RIUP24/2433/JANARDAN ORGANICF/UBIN0565750 396000.00
52794 | [17 empty] | 0 | 400000 | 396000 | 14-11-2024 NEFT/AXISP00569818228/RIUP24/2452/JANARDAN ORGANICF/UBIN0565750 396000.00
52794 | [17 empty] | 0 | 300000 | 297000 | 22-11-2024 NEFT/AXISP00573604260/RIUP24/2488/JANARDAN ORGANIC F/UBIN0565750 297000.00
52796 | thirwa | oht work | Thirwa Village OHT work | [10 empty] | 0
52796 | [17 empty] | 0 | 500000 | 495000 | 01/03/2023 NEFT/AXISP00367587604/RIUP22/2401/JANARD 495000.00
52796 | [17 empty] | 0 | 500000 | 495000 | 29-10-2024 NEFT/AXISP00560462659/RIUP24/2288/JANARDAN ORGANICF/UBIN0565750 495000.00
53217 | bidauli | 300 kl 14 mtr work | Bidauli village 300 KL 14 mtr work | 2023-07-19 | 32188 | 756000 |  | 756000 | 136080 | 892080 | 7560 | 37800 |  | 0 | 136080 |  | 635040 | 0 | 500000 | 495000 | 08-03-2023 NEFT/AXISP00369766184/RIUP22/2495/JANARDAN ORGANI 495000.00
53217 | bidauli | 300 kl 14 mtr work | Bidauli village 300 KL 14 mtr work | 2023-10-14 | 109, 250 | 378000 | 175696.36 | 202303.64 | 36414.66 | 238718.3 | 2023.04 | 10115.18 |  | 0 | 36414.66 |  | 169935.06 | 0 | 150000 | 148500 | 04-11-2023 NEFT/AXISP00440433096/RIUP23/3067/JANARDAN ORGANIC F/UBIN0565750 148500.00
53217 | bidauli | 300 kl 14 mtr work | Bidauli village 300 KL 14 mtr work | 2023-12-08 | 140, 24 | 378000 | 96375.92 | 281624.08 | 50692.33 | 332316.41 | 2816.24 | 14081.2 |  | 0 | 50692.33 |  | 236564.23 | 0 | 250000 | 247500 | 24-11-2023 NEFT/AXISP00446428098/RIUP23/3427/JANARDAN ORGANICF/UBIN0565750 247500.00
53217 | [17 empty] | 0 | 300000 | 297000 | 27-08-2024 NEFT/AXISP00532290647/RIUP24/1539/JANARDAN ORGANICF/UBIN0565750 297000.00
53217 | [17 empty] | 0 | 600000 | 594000 | 01-10-2024 NEFT/AXISP00547359346/RIUP24/2024/JANARDAN ORGANICF/UBIN0565750 594000.00
53217 | [17 empty] | 0 | 500000 | 495000 | 29-10-2024 NEFT/AXISP00559829077/RIUP24/2287/JANARDAN ORGANICF/UBIN0565750 495000.00
56007 | rajhar | 350 kl 14 mtr work | Rajhar Village 350 KL 14 mtr work | 2023-03-27 | 28 | 425182.3 | 168709.9 | 256472 | 46165 | 302637 | 2565 | 12824 | 0 | 0 | 46165 |  | 215436 | 0 | 215436 | 215436 | 19-04-2023 19-04-2023 NEFT/AXISP00382928308/SPUP23/0186/JANARDAN ORGANI 215436.00
56007 |  |  | GST Release Note |  | 28 | 46165 | [10 empty] | 46165 | 0 | 200000 | 198000 | 28-06-2023 NEFT/AXISP00401570068/RIUP23/941/JANARDAN ORGANIC ₹ 1,98,000.00
56007 | rajhar | 350 kl 14 mtr work | Rajhar Village 350 KL 14 mtr work | 2023-04-15 | 11 | 425182.3 |  | 425182 | 76533 | 501715 | 4252 | 21259 | 0 | 0 | 76533 |  | 357153 | 0 | 357153 | 357153 | 19-04-2023 19-04-2023 NEFT/AXISP00382928309/SPUP23/0187/JANARDAN ORGANI 357153.00
56007 |  |  | GST Release Note |  | 11 | 76533 | [10 empty] | 76533 | 0 | 200000 | 198000 | 18-07-2023 NEFT/AXISP00407734316/RIUP23/1138/JANARDAN ORGANI 198000.00
56007 | rajhar | 350 kl 14 mtr work | Rajhar Village 350 KL 14 mtr work | 2023-09-13 | 84, 185, & 217 | 850364 | 370346 | 480018 | 86403 | 566421 | 4800 | 24001 | 0 | 0 | 86403 |  | 403215 | 0 | 100000 | 99000 | 28-07-2023 NEFT/AXISP00410084838/RIUP23/1265/JANARDAN ORGANI 99000.00
56007 |  |  | GST Release Note |  | 84, 185, & 217 | 86403 | [10 empty] | 86403 | 0 | 100000 | 99000 | 13-12-2023 NEFT/AXISP00452475687/RIUP23/3704/JANARDAN ORGANICF/UBIN0565750 99000.00
56007 | rajhar | 350 kl 14 mtr work | Rajhar Village 350 KL 14 mtr work | 2024-01-16 | 41, 158 | 425182 | 412911 | 12271 | 2209 | 14480 | 123 | 614 | 0 | 0 | 2209 |  | 10307 | 0 | 500000 | 495000 | 01-06-2024 NEFT/AXISP00505116439/RIUP24/0731/JANARDAN ORGANIC F/UBIN0565750 495000.00
56007 |  |  | GST Release Note |  | 41, 158 | 2209 | [10 empty] | 2209 | 0 | 400000 | 396000 | 24-09-2024 NEFT/AXISP00543503652/RIUP24/1911/JANARDAN ORGANICF/UBIN0565750 396000.00
56007 | [17 empty] | 0 | 800000 | 792000 | 01-10-2024 NEFT/AXISP00547359347/RIUP24/2025/JANARDAN ORGANICF/UBIN0565750 792000.00
56007 | [17 empty] | 0 | 500000 | 495000 | 05-10-2024 NEFT/AXISP00549508646/RIUP24/2129/JANARDAN ORGANIC F/UBIN0565750 ₹ 4,95,000.00
56007 | [17 empty] | 0 | 200000 | 198000 | 17-10-2024 NEFT/AXISP00554849807/RIUP24/2223/JANARDAN ORGANICF/UBIN0565750 198000.00
56007 | [17 empty] | 0 | 300000 | 297000 | 08-11-2024 NEFT/AXISP00566570855/RIUP24/2432/JANARDAN ORGANICF/UBIN0565750 297000.00
56007 | [17 empty] | 0 | 300000 | 297000 | 30-12-2024 Debit N/RIUP24/2767/JANARDAN ORGAN/INDBN30124223032 297000.0
56009 | kajipur thirwa | 250kl 12 m oht construction work | Kajipur Thirwa Village 250kl 12 m OHT Construction work | 2023-03-27 | 27 | 309731.4 | 231489.49 | 78242 | 14084 | 92326 | 782 | 3912 | 0 | 0 | 14084 |  | 65724 | 0 | 100000 | 99000 | 12-06-2023 NEFT/AXISP00397581454/RIUP23/579/JANARDAN ORGANIC 99000.00
56009 |  |  | GST Release Note |  | 27 | 14084 | [10 empty] | 14084 | 0 | 300000 | 297000 | 13-12-2023 NEFT/AXISP00452475689/RIUP23/3706/JANARDAN ORGANICF/UBIN0565750 297000.00
56009 | kajipur thirwa | 250kl 12 m oht construction work | Kajipur Thirwa Village 250kl 12 m OHT Construction work | 2023-03-31 | 35 | 309731.4 | 0 | 309731 | 55752 | 365483 | 3097 | 15487 | 0 | 0 | 55752 |  | 260174 | 0 | 100000 | 99000 | 13-06-2023 NEFT/AXISP00398124635/RIUP23/651/JANARDAN ORGANIC 99000.00
56009 |  |  | GST Release Note |  | 35 | 55752 | [10 empty] | 55752 | 0 | 1000000 | 950000 | 30-05-2024 NEFT/AXISP00503666361/RIUP24/0652/JANARDAN ORGANICF/UBIN0565750 950000.00
56009 | kajipur thirwa | 250kl 12 m oht construction work | Kajipur Thirwa Village 250kl 12 m OHT Construction work | 2023-07-19 | 31, 187 | 682500 | 380669.02 | 301831 | 54330 | 356161 | 3018 | 15092 |  | 0 | 54330 |  | 253538 | 0 | 200000 | 198000 | 01-07-2023 NEFT/AXISP00402764249/RIUP23/975/JANARDAN ORGANIC 198000.00
56009 |  |  | GST Release Note |  | 31, 187 | 54330 | [10 empty] | 54330 | 0 | 200000 | 198000 | 19-09-2024 NEFT/AXISP00542202590/RIUP24/1855/JANARDAN ORGANICF/UBIN0565750 198000.00
56009 | kajipur thirwa | 250kl 12 m oht construction work | Kajipur Thirwa Village 250kl 12 m OHT Construction work | 2023-11-07 | 129, 11 | 341250 | 316350 | 24900 | 4482 | 29382 | 249 | 1245 |  | 0 | 4482 |  | 20916 | 0 | 500000 | 495000 | 01-10-2024 NEFT/AXISP00547359348/RIUP24/2026/JANARDAN ORGANICF/UBIN0565750 495000.00
56009 | kajipur thirwa | 250kl 12 m oht construction work | Kajipur Thirwa Village 250kl 12 m OHT Construction work | 2024-01-16 | 160, 39 | 511875 | 510547 | 1328 | 239 | 1567 | 13 | 66 |  | 0 | 239 |  | 1116 | 0 | 500000 | 495000 | 16-10-2024 NEFT/AXISP00554277922/RIUP24/2222/JANARDAN ORGANICF/UBIN0565750 495000.00
56009 |  |  | GST Release Note |  | 160, 39 | 239 | [10 empty] | 239
59284 | khera bhau singhalika | 150 kl 160 mtr work | Khera Bhau Singhalika village 150 Kl 160 mtr work | 2023-09-14 | 88230 | 130500 | 0 | 130500 | 23490 | 153990 | 1305 | 6525 | 0 | 0 | 23490 |  | 122670 | 0 | 150000 | 148500 | 22-09-2023 NEFT/AXISP00426907970/RIUP23/2209/JANARDAN ORGANIC F/UBIN0565750 148500.00
59284 |  |  | GST Release Note |  | 88230 | 23490 | [10 empty] | 23490 | 0 | 400000 | 396000 | 01-08-2024 NEFT/AXISP00523998745/RIUP24/1337/JANARDAN ORGANICF/UBIN0565750 396000.00
59284 | khera bhau singhalika | 150 kl 160 mtr work | Khera Bhau Singhalika village 150 Kl 160 mtr work | 2023-10-23 | 116, 1 | 261000 | 148437 | 112563 | 20261 | 132824 | 1126 | 5628 | 0 | 0 | 20261 |  | 105809 | 0 | 150000 | 148500 | 07-12-2023 NEFT/AXISP00450593583/RIUP23/3642/JANARDAN ORGANIC F/UBIN0565750 1,48,500.00
59284 |  |  | GST Release Note |  | 116, 1 | 20261 | [10 empty] | 20261 | 0 | 500000 | 495000 | 18-07-2024 NEFT/AXISP00519648697/RIUP24/1149/JANARDAN ORGANIC F/UBIN0565750 ₹ 4,95,000.00
59284 | khera bhau singhalika | 150 kl 160 mtr work | Khera Bhau Singhalika village 150 Kl 160 mtr work | 2023-10-23 | 145,26 | 652500 | 173674.17 | 478826 | 86189 | 565015 | 4788 | 23941 | 0 | 0 | 86189 |  | 450097 | 0 | 500000 | 475000 | 25-04-2024 NEFT/AXISP00493861225/RIUP24/0311/JANARDAN ORGANICF/UBIN0565750 475000.00
59284 |  |  | GST Release Note |  | 145,26 | 86189 | [10 empty] | 86189 | 0 | 500000 | 475000 | 18-05-2024 NEFT/AXISP00501160943/RIUP24/0568/JANARDAN ORGANICF/UBIN0565750 475000.00
59285 | panthupura | 225 kl 16 mtr work | Panthupura Village 225 KL 16 Mtr work | 2023-09-14 | 89, 232 | 166500 | 0 | 166500 | 29970 | 196470 | 1665 | 8325 | 0 | 0 | 29970 |  | 139860 | 0 | 200000 | 198000 | 27-09-2023 NEFT/AXISP00427962780/RIUP23/2341/JANARDAN ORGANIC F/UBIN0565750 198000.00
59285 |  |  | GST Release Note |  | 89, 232 | 29970 | [10 empty] | 29970 | 0 | 200000 | 198000 | 21-03-2024 NEFT/AXISP00483037811/RIUP23/5230/JANARDAN ORGANICF/UBIN0565750 198000.00
59285 | panthupura | 225 kl 16 mtr work | Panthupura Village 225 KL 16 Mtr work | 2023-10-23 | 115, 2 | 333000 | 152205 | 180795 | 32543 | 213338 | 1808 | 9040 | 0 | 0 | 32543 |  | 169947 | 0 | 200000 | 190000 | 04-05-2024 NEFT/AXISP00496939374/RIUP24/0389/JANARDAN ORGANICF/UBIN0565750 190000.00
59285 |  |  | GST Release Note |  | 115, 2 | 32543 | [10 empty] | 32543 | 0 | 200000 | 198000 | 30-11-2023 NEFT/AXISP00447919700/RIUP23/3543/JANARDAN ORGANIC F/UBIN0565750 198000.00
59285 | [17 empty] | 0 | 200000 | 198000 | 31-07-2024 NEFT/AXISP00522546967/RIUP24/1271/JANARDAN ORGANICF/UBIN0565750 198000.00
59285 | [17 empty] | 0 | 500000 | 495000 | 23-08-2024 NEFT/AXISP00531577845/SKUP24/159/JANARDAN ORGANIC F/UBIN0565750 495000.00
59285 | [17 empty] | 0 | 300000 | 297000 | 17-09-2024 NEFT/AXISP00541269862/RIUP24/1816/JANARDAN ORGANICF/UBIN0565750 297000.00
59285 | [17 empty] | 0 | 200000 | 198000 | 04-10-2024 NEFT/AXISP00548955244/RIUP24/2117/JANARDAN ORGANICF/UBIN0565750 198000.00
59286 | nanagli | 2245 kl 14 mtr work | Nanagli village 2245 KL 14 mtr work | 2023-09-14 | 90, 231 | 162000 | 0 | 162000 | 29160 | 191160 | 1620 | 8100 | 0 | 0 | 29160 |  | 152280 | 0 | 150000 | 148500 | 22-09-2023 NEFT/AXISP00426907971/RIUP23/2210/JANARDAN ORGANIC F/UBIN0565750 148500.00
59286 | nanagli | 2245 kl 14 mtr work | Nanagli village 2245 KL 14 mtr work | 2023-10-05 | 104, 245 | 324000 | 111576 | 212424 | 38236 | 250660 | 2124 | 10621 | 0 | 0 | 38236 |  | 199679 | 0 | 300000 | 297000 | 09-10-2023 NEFT/AXISP004269087465/RIUP23/2598/JANARDAN ORGANIC F/UBIN0565750 297000.00
59286 |  |  | GST Release Note |  | 104, 245 | 38236 | [10 empty] | 38236 | 0 | 500000 | 495000 | 02-01-2024 NEFT/AXISP00458541610/RIUP23/4076/JANARDAN ORGANIC F/UBIN0565750 495000.00
59286 | nanagli | 2245 kl 14 mtr work | Nanagli village 2245 KL 14 mtr work | 2023-12-28 | 146, 27 | 810000 | 154255 | 655745 | 118034 | 773779 | 6557 | 32787 | 0 | 0 | 118034 |  | 616401 | 0 | 250000 | 247500 | 24-11-2023 NEFT/AXISP00446428099/RIUP23/3428/JANARDAN ORGANICF/UBIN0565750 247500.00
59286 |  |  | GST Release Note |  | 146, 27 | 118034 | [10 empty] | 118034 | 0 | 500000 | 475000 | 24-05-2024 NEFT/AXISP00502671116/RIUP24/0604/JANARDAN ORGANICF/UBIN0565750 475000.00
59286 | [17 empty] | 0 | 300000 | 297000 | 26-12-2024 Debit N/RIUP24/2768/JANARDAN ORGAN/INDBN26123786891 297000.0
59987 | islampur ghausali | 325 kl 16 mtr work | Islampur Ghausali village 325 KL 16 Mtr work | 2023-10-23 | 117, 3 | 628875 | 297324 | 331551 | 59679.18 | 391230.18 | 3316 | 16578 | 0 | 0 | 59679.18 |  | 311657 | 0 | 300000 | 297000 | 30-11-2023 NEFT/AXISP00447919701/RIUP23/3544/JANARDAN ORGANIC F/UBIN0565750 297000.00
59987 |  |  | GST Release Note |  | 117, 3 | 59679.18 | [10 empty] | 59679.18 | 0 | 300000 | 297000 | 04-12-2023 NEFT/AXISP00447851236/RIUP23/3591/JANARDAN ORGANIC F/UBIN0565750 297000.00
59987 | [17 empty] | 0 | 200000 | 198000 | 29-03-2024 NEFT/AXISP00485733267/RIUP23/5309/JANARDAN ORGANIC F/UBIN0565750 ₹ 1,98,000.00
59987 | [17 empty] | 0 | 500000 | 475000 | 26-04-2024 NEFT/AXISP00493934371/RIUP24/0323/JANARDAN ORGANICF/UBIN0565750 475000.00
59987 | [17 empty] | 0 | 500000 | 495000 | 19-07-2024 NEFT/AXISP00519907623/RIUP24/1183/JANARDAN ORGANICF/UBIN0565750 495000.00
59987 | [17 empty] | 0 | 300000 | 297000 | 31-07-2024 NEFT/AXISP00522546968/RIUP24/1272/JANARDAN ORGANICF/UBIN0565750 297000.00
59987 | [17 empty] | 0 | 500000 | 495000 | 23-08-2024NEFT/AXISP00531577846/SKUP24/165/JANARDAN ORGANICF/UBIN0565750 495000.00
59987 | [17 empty] | 0 | 500000 | 495000 | 04-09-2024 NEFT/AXISP00535970653/RIUP24/1611/JANARDAN ORGANIC F/UBIN0565750 ₹ 4,95,000.00
59987 | [17 empty] | 0 | 200000 | 198000 | 24-09-2024 NEFT/AXISP00543503651/RIUP24/1910/JANARDAN ORGANICF/UBIN0565750 198000.00
59987 | [17 empty] | 0 | 500000 | 495000 | 04-10-2024 NEFT/AXISP00548955242/RIUP24/2116/JANARDAN ORGANICF/UBIN0565750 495000.00
59987 | [17 empty] | 0 | 200000 | 198000 | 11-10-2024 NEFT/AXISP00552724055/RIUP24/2187/JANARDAN ORGANIC F/UBIN0565750 198000.0
60117 | ballamazara | 225 kl 12 mtr work | Ballamazara village 225 KL 12 Mtr work | 2023-11-07 | 130,12 | 472500 | 241465 | 231035 | 41586.3 | 272621.3 | 2310.35 | 11551.75 |  | 0 | 41586.3 |  | 194069.4 | 0 | 100000 | 99000 | 30-11-2023 NEFT/AXISP00447919702/RIUP23/3545/JANARDAN ORGANIC F/UBIN0565750 99000.00
60117 |  |  | GST Release Note |  | 130,12 | 41586.3 | [10 empty] | 41586.3 | 0 | 100000 | 99000 | 11-12-2023 NEFT/AXISP00451739033/RIUP23/3687/JANARDAN ORGANICF/UBIN0565750 99000.00
60117 | [17 empty] | 0 | 200000 | 190000 | 14-05-2024 NEFT/AXISP00499706370/RIUP24/0480/JANARDAN ORGANICF/UBIN0565750 190000.00
60117 | [17 empty] | 0 | 500000 | 495000 | 19-07-2024 NEFT/AXISP00519907624/RIUP24/1184/JANARDAN ORGANICF/UBIN0565750 495000.00
60117 | [17 empty] | 0 | 300000 | 297000 | 26-07-2024 NEFT/AXISP00521556657/RIUP24/1258/JANARDAN ORGANICF/UBIN0565750 297000.00
60117 | [17 empty] | 0 | 200000 | 198000 | 03-09-2024 NEFT/AXISP00535722995/RIUP24/1610/JANARDAN ORGANICF/UBIN0565750 198000.00
60117 | [17 empty] | 0 | 300000 | 297000 | 03-10-2024 NEFT/AXISP00548259337/RIUP24/2094/JANARDAN ORGANICF/UBIN0565750 297000.00
60117 | [17 empty] | 0 | 300000 | 297000 | 04-10-2024 NEFT/AXISP00548955240/RIUP24/2115/JANARDAN ORGANICF/UBIN0565750 297000.00
60117 | [17 empty] | 0 | 200000 | 198000 | 11-10-2024 NEFT/AXISP00552724054/RIUP24/2186/JANARDAN ORGANIC F/UBIN0565750 198000.0
60810 | khertu | 225 kl 12 mtr work | Khertu village 225 KL 12 mtr work | 2023-12-08 | 141, 22 | 472500 | 277584 | 194916 | 35084.88 | 230000.88 | 1949.16 | 9745.8 |  | 0 | 35084.88 |  | 163729.44 | 0 | 150000 | 148500 | 21-12-2023 NEFT/AXISP00454518236/RIUP23/3880/JANARDAN ORGANICF/UBIN0565750 148500.00
60810 |  |  | GST Release Note |  | 141, 22 | 35084.88 | [10 empty] | 35084.88 | 0 | 1000000 | 990000 | 10-01-2024 NEFT/AXISP00461403096/RIUP23/4221/JANARDAN ORGANIC F/UBIN0565750 990000.00
60810 | khertu | 225 kl 12 mtr work | Khertu village 225 KL 12 mtr work | 2024-01-16 | 159, 38 | 787500 | 786996 | 504 | 90.72 | 594.72 | 5.04 | 25.2 |  | 0 | 90.72 |  | 423.36 | 0 | 500000 | 495000 | 06-01-2024 NEFT/AXISP00460249929/RIUP23/4144/JANARDAN ORGANICF/UBIN0565750 495000.00
60810 |  |  | GST Release Note |  | 159, 38 | 90.72 | [10 empty] | 90.72 | 0 | 200000 | 198000 | 31-07-2024 NEFT/AXISP00522966394/RIUP24/1303/JANARDAN ORGANICF/UBIN0565750 198000.00
60810 | [17 empty] | 0 | 200000 | 198000 | 13-09-2024 NEFT/AXISP00540414561/RIUP24/1779/JANARDAN ORGANICF/UBIN0565750 198000.00
60810 | [17 empty] | 0 | 100000 | 99000 | 19-09-2024 NEFT/AXISP00542202587/RIUP24/1858/JANARDAN ORGANICF/UBIN0565750 99000.00
60811 | harsana | 225 kl 12 mtr work | Harsana village 225 KL 12 mtr work | 2023-12-08 | 142, 23 | 472500 | 276596 | 195904 | 35262.72 | 231166.72 | 1959.04 | 9795.2 |  | 0 | 35262.72 |  | 164559.36 | 0 | 150000 | 148500 | 21-12-2023 NEFT/AXISP00454518237/RIUP23/3881/JANARDAN ORGANICF/UBIN0565750 148500.00
60811 |  |  | GST Release Note |  | 142, 23 | 35262.72 | [10 empty] | 35262.72 | 0 | 500000 | 495000 | 06-01-2024 NEFT/AXISP00460249928/RIUP23/4145/JANARDAN ORGANICF/UBIN0565750 495000.00
60811 | [17 empty] | 0 | 500000 | 475000 | 25-04-2024 NEFT/AXISP00493861228/RIUP24/0314/JANARDAN ORGANICF/UBIN0565750 475000.00
60811 | [17 empty] | 0 | 200000 | 198000 | 03-09-2024 NEFT/AXISP00535722994/RIUP24/1609/JANARDAN ORGANIC F/UBIN0565750 198000.00
60811 | [17 empty] | 0 | 200000 | 198000 | 11-10-2024 NEFT/AXISP00552723371/RIUP24/2185/JANARDAN ORGANIC F/UBIN0565750 198000.00
60814 | bhogimazra | 100 kl 10 mtr work | Bhogimazra village 100 KL 10 Mtr work | 2023-12-08 | 143, 21 | 285000 | 214252 | 70748 | 12734.64 | 83482.64 | 707.48 | 3537.4 |  | 0 | 12734.64 |  | 59428.32 | 0 | 500000 | 495000 | 21-12-2023 NEFT/AXISP00454518238/RIUP23/3882/JANARDAN ORGANICF/UBIN0565750 495000.00
60814 |  |  | GST Release Note |  | 143, 21 | 12734.64 | [10 empty] | 12734.64 | 0 | 500000 | 495000 | 09-01-2024 NEFT/AXISP00460826673/RIUP23/4169/JANARDAN ORGANICF/UBIN0565750 495000.00
60814 | [17 empty] | 0 | 500000 | 495000 | 19-07-2024 NEFT/AXISP00519907625/RIUP24/1185/JANARDAN ORGANICF/UBIN0565750 495000.00
62071 | gandharv | 300 kl 12 mtr work | Gandharv village 300 KL 12 mtr work | 2024-01-16 | 161, 40 | 367500 | 365387.5 | 2112.5 | 380.25 | 2492.75 | 21.13 | 105.63 |  | 0 | 380.25 |  | 1985.75 | 0 | 500000 | 475000 | 25-04-2024 NEFT/AXISP00493861227/RIUP24/0313/JANARDAN ORGANICF/UBIN0565750 475000.000
62071 |  |  | GST Release Note |  | 161, 40 | 380.25 | [10 empty] | 380.25 | 0 | 500000 | 475000 | 25-04-2024 NEFT/AXISP00493861227/RIUP24/0313/JANARDAN ORGANICF/UBIN0565750 475000.00
62071 | [17 empty] | 0 | 400000 | 380000 | 04-05-2024 NEFT/AXISP00496939375/RIUP24/0390/JANARDAN ORGANICF/UBIN0565750 380000.00
62071 | [17 empty] | 0 | 1000000 | 990000 | 27-06-2024 NEFT/AXISP00512319351/RIUP24/0940/JANARDAN ORGANICF/UBIN0565750 990000.00
62071 | [17 empty] | 0 | 500000 | 495000 | 19-07-2024 NEFT/AXISP00519907626/RIUP24/1186/JANARDAN ORGANICF/UBIN0565750 495000.00
62071 | [17 empty] | 0 | 300000 | 297000 | 03-09-2024 NEFT/AXISP00535722993/RIUP24/1608/JANARDAN ORGANICF/UBIN0565750 297000.00
62071 | [17 empty] | 0 | 200000 | 198000 | 20-09-2024 NEFT/AXISP00542641365/RIUP24/1877/JANARDAN ORGANICF/UBIN0565750 198000.00
62330 | bharsi | 300 kl 12 mtr work | Bharsi village 300 Kl 12 mtr work | [10 empty] | 0
62330 | [17 empty] | 0 | 500000 | 495000 | 06-03-2024 NEFT/AXISP00477669928/RIUP23/5005/JANARDAN ORGANICF/UBIN0565750 495000.00
62330 | [17 empty] | 0 | 1000000 | 990000 | 16-04-2024 NEFT/AXISP00491676959/RIUP24/0164/JANARDAN ORGANICF/UBIN0565750 990000.00
62330 | [17 empty] | 0 | 1000000 | 990000 | 06-06-2024 NEFT/AXISP00506791469/RIUP24/0772/JANARDAN ORGANIC F/UBIN0565750 990000.00
62330 | [17 empty] | 0 | 500000 | 495000 | 11-07-2024 NEFT/AXISP00517806264/RIUP24/1088/JANARDAN ORGANICF/UBIN0565750 495000.00
62330 | [17 empty] | 0 | 500000 | 495000 | 19-07-2024 NEFT/AXISP00519907628/RIUP24/1187/JANARDAN ORGANICF/UBIN0565750 495000.00
62331 | jasala | 425 kl 12 mtr work | Jasala village 425 KL 12 mtr work | [10 empty] | 0
62331 | [17 empty] | 0 | 500000 | 495000 | 06-03-2024 NEFT/AXISP00477669929/RIUP23/5006/JANARDAN ORGANICF/UBIN0565750 495000.00
62331 | [17 empty] | 0 | 1000000 | 990000 | 16-04-2024 NEFT/AXISP00491676958/RIUP24/0165/JANARDAN ORGANICF/UBIN0565750 990000.00
62331 | [17 empty] | 0 | 500000 | 475000 | 24-05-2024 NEFT/AXISP00502671115/RIUP24/0605/JANARDAN ORGANICF/UBIN0565750 475000.00
62331 | [17 empty] | 0 | 1000000 | 990000 | 06-06-2024 NEFT/AXISP00506791470/RIUP24/0773/JANARDAN ORGANICF/UBIN0565750 990000.00
62331 | [17 empty] | 0 | 500000 | 495000 | 11-07-2024 NEFT/AXISP00517806265/RIUP24/1089/JANARDAN ORGANICF/UBIN0565750 495000.00
62331 | [17 empty] | 0 | 500000 | 495000 | 19-07-2024 NEFT/AXISP00519907629/RIUP24/1188/JANARDAN ORGANICF/UBIN0565750 495000.00
62331 | [17 empty] | 0 | 300000 | 297000 | 20-09-2024 NEFT/AXISP00542641364/RIUP24/1876/JANARDAN ORGANICF/UBIN0565750 297000.00
62332 | nanupuri | 50 kl 12 mtr work | Nanupuri village 50 KL 12 mtr work | [10 empty] | 0
62332 | [17 empty] | 0 | 500000 | 495000 | 18-03-2024 NEFT/AXISP00481766498/RIUP23/5161/JANARDAN ORGANICF/UBIN0565750 495000.00
62332 | [17 empty] | 0 | 500000 | 475000 | 24-05-2024 NEFT/AXISP00502671114/RIUP24/0606/JANARDAN ORGANICF/UBIN0565750 475000.00
62332 | [17 empty] | 0 | 200000 | 198000 | 20-09-2024 NEFT/AXISP00542641363/RIUP24/1875/JANARDAN ORGANICF/UBIN0565750 198000.00
TOTAL | [5 empty] | 30794312.54 |  |  |  |  | 156055.21 | 780281 | 121430.84 |  |  | 173984 | 15549523.85 |  |  | 73404341
Contractor Name | A K Saini Construction
Date | Friday, 2025-05-16
Description | Amount
Advance/Surplus | -57854817.15
Total Hold Amount | 173984
Amount With TDS | 156055.21000000005