## Contractor Report
Contractor Name | Balaji construction
State
District
Block
Mobile No
GST Type
GST No
PAN No
Email
Address
PMC No | Village | Work Type | Invoice Details | Invoice Date | Invoice No | Basic Amount | Debit | After Debit Amount | GST (18%) | Amount | TDS (1%) | SD (5%) | On Commission | Hydro Testing | GST SD Amount | Hold Amount For Material | Final Amount | Payment Amount | TDS Payment | Total Paid | UTR
53361 | sohajani jatan | pipe laying work | Sohajani Jatan Village Pipe laying work | 2022-12-12 | 6 | 312091 | 80919 | 231172 | 41611 | 272783 | 2311.72 | 11558.6 | 23117.2 | 23117.2 | 41611 |  | 161590 | 0 | 0 | 161590 | 26-12-2022 NEFT/AXISP00348647834/RIUP22/1620/A K SAINI CONST 161590.00
53361 |  |  | GST Release Note |  | 6 | 41611 | [10 empty] | 41611
51556 | meghakheri | pipe laying work | Meghakheri Village Pipe laying work | 2022-10-01 | 4 | 1272181.45 | 139987 | 1132194 | 203795 | 1335989 | 11321.94 | 56609.7 | 56609.7 | 113219.4 | 203795 |  | 797335 | 0 | 0 | 495000 | 10-10-2022 NEFT/AXISP00327017850/RIUP22/928/A K SAINI CONSTR 495000.00
51556 | meghakheri | pipe laying work | Meghakheri Village Pipe laying work | 2022-11-14 | 5 | 559849.95 | 33267 | 526583 | 94785 | 621368 | 5265.83 | 26329.15 | 26329.15 | 52658.3 | 94785 |  | 348592 | 0 | 0 | 297000 | 12-10-2022 NEFT/AXISP00327681886/RIUP22/967/A K SAINI CONSTR 297000.00
51556 |  |  | GST Release Note |  | 5 | 298580 | [10 empty] | 298580 | 0 | 0 | 5335 | 20-10-2022 NEFT/AXISP00330028514/RIUP22/1042/A K SAINI CONST 5335.00
51556 | [17 empty] | 0 | 0 | 148500 | 14-11-2022 NEFT/AXISP00337247388/RIUP22/1241/A K SAINI CONST 148500.00
51556 | [17 empty] | 0 | 0 | 200092 | 22-11-2022 NEFT/AXISP00339527007/RIUP22/1286/A K SAINI CONST 200092.00
51555 | faloda | pipe laying work | Faloda Village Pipe laying work | 2022-08-05 | 3 | 381511.76 | 74016 | 307495.76 | 55349 | 362844.76 | 3074.96 | 15374.79 | 15374.79 | 30749.58 | 55349 |  | 242922 | 0 | 0 | 242921 | 24-08-2022 NEFT/AXISP00314017487/RIUP22/496/A K SAINI CONSTR 242921.00
51555 |  |  | GST Release Note |  | 3 | 55349 | [10 empty] | 55349
57752 | khokani | pipeline work | Khokani Village Pipeline work | 2023-07-07 | 1 | 218144 | 0 | 218144 | 39266 | 257410 | 2181.44 | 10907.2 | 10907.2 | 21814.4 | 39266 | 0 | 172334 | 150000 | 1500 | 148500 | 12-07-2023 NEFT/AXISP00406496251/RIUP23/1062/BALAJI CONSTRUC ₹ 1,48,500.00
57752 | khokani | pipeline work | Khokani Village Pipeline work | 2023-11-06 | 8 | 225997 | 7600 | 218397 | 39311.46 | 257708.46 | 2183.97 | 10919.85 | 21839.7 | 21839.7 | 39311.46 | 15666 | 145947.78 | 23835 | 0 | 23835 | 21-07-2023 NEFT/AXISP00408446742/RIUP23/1097/BALAJI CONSTRUC 23835.00
57752 |  |  | GST Release Note |  | 8 | 78577.46 | [10 empty] | 78577.46 | 46947 | 0 | 46947 | 01-12-2023 NEFT/AXISP00448665328/RIUP23/3474/BALAJI CONSTRUCTIO/UBIN0572632 ₹ 46,947.00
57752 | khokani | pipeline work | Khokani Village Pipeline work | 2024-01-13 | 10 | 432896 | 0 | 432896 | 77921.28 | 510817.28 | 4328.96 | 21644.8 | 43289.6 | 43289.6 | 77921.28 | 0 | 320343.04 | 100000 | 1000 | 99000 | 10-11-2023 NEFT/AXISP00443237220/RIUP23/3218/BALAJI CONSTRUCTIO/UBIN0572632 99000.00
57752 |  |  | GST Release Note |  | 10 | 77921.28 | [10 empty] | 77921.28 | 320342 | 0 | 320342 | 25-01-2024 NEFT/AXISP00464876202/RIUP23/4419/BALAJI CONSTRUCTIO/UBIN0572632 320342.00
57752 | [19 empty] | 78577 | 30-03-2024 NEFT/AXISP00486493289/RIUP23/4841/BALAJI CONSTRUCTIO/UBIN0572632 78577.00
57938 | khokani | pump house work | Khokani Village Pump house work | 2023-07-07 | 2 | 105000 | 56170 | 48830 | 8789 | 57619 | 488.3 | 4883 |  |  | 8789 | 0 | 43459 | 43459 | 0 | 43459 | 14-07-2023 NEFT/AXISP00406995905/RIUP23/1072/BALAJI CONSTRUC 43459.00
57938 |  |  | GST Release Note |  | 2 | 8789 | [10 empty] | 8789 |  |  | 8789 | 06-03-2024 NEFT/AXISP00477945203/RIUP23/4842/BALAJI CONSTRUCTIO/UBIN0572632 8789.00
57938 | khokani | pump house work | Khokani Village Pump house work | 2023-09-26 | 6 | 210000 | 0 | 210000 | 37800 | 247800 | 2100 | 21000 |  |  | 37800 |  | 186900 | 186900 | 0 | 186900 | 17-10-2023 NEFT/AXISP00435088305/RIUP23/2421/BALAJI CONSTRUCTIO/UBIN0572632 186900.00
57938 |  |  | GST Release Note |  | 6 | 37800 | [10 empty] | 37800
58241 | khokani | boundary wall work | Khokani Village Boundary wall work | 2023-07-07 | 3 | 144900 | 0 | 144900 | 26082 | 170982 | 1449 | 7245 |  |  | 26082 |  | 136206 | 136206 | 0 | 136206 | 15-07-2023 NEFT/AXISP00407289885/RIUP23/1094/BALAJI CONSTRUC ₹ 1,36,206.00
58241 | khokani | boundary wall work | Khokani Village Boundary wall work | 2023-09-26 | 5 | 139300 | 0 | 139300 | 25074 | 164374 | 1393 | 6965 |  |  | 25074 |  | 130942 | 130942 | 0 | 130942 | 17-10-2023 NEFT/AXISP00435088306/RIUP23/2422/BALAJI CONSTRUCTIO/UBIN0572632 130942.00
58241 |  |  | GST Release Note |  | 5 | 51156 | [10 empty] | 51156 |  |  | 51156 | 30-03-2024 NEFT/AXISP00486493282/RIUP23/4839/BALAJI CONSTRUCTIO/UBIN0572632 51156.00
58486 | randawali , jhabarpur,harinagar | pipeline work | Randawali , Jhabarpur,Harinagar Village Pipeline work | 2023-08-10 | 4 | 470584 | 0 | 470584 | 84705 | 555289 | 4705.84 | 23529.2 | 23529.2 | 47058.4 | 84705 | 1180 | 370581 | 370582 | 0 | 370582 | 14-08-2023 NEFT/AXISP00415803578/RIUP23/1497/BALAJI CONSTRUC ₹ 3,70,582.00
58486 | randawali , jhabarpur,harinagar | pipeline work | Randawali , Jhabarpur,Harinagar Village Pipeline work | 2023-10-14 | 7 | 691770.5 | 4560 | 687211 | 123698 | 810909 | 6872.11 | 34360.55 | 34360.55 | 68721.1 | 123698 | 23007 | 519890 | 51988 | 0 | 519888 | 26-10-2023 NEFT/AXISP00437006020/RIUP23/2845/BALAJI CONSTRUCTIO/UBIN0572632 519888.00
58486 |  |  | GST Release Note |  | 7 | 208403 | [10 empty] | 208403 | 20843 | 208.43 | 208403 | 28-02-2024 NEFT/AXISP00474588154/RIUP23/4840/BALAJI CONSTRUCTIO/UBIN0572632 208403.00
58486 | randawali , jhabarpur,harinagar | pipeline work | Randawali , Jhabarpur,Harinagar Village Pipeline work | 2024-02-13 | 11 | 1592282 | 0 | 1592282 | 286611 | 1878893 | 15922.82 | 79614.1 | 159228.2 | 159228.2 | 286611 | 114693 | 1063596 | 200000 | 2000 | 198000 | 27-12-2023 NEFT/AXISP00455794960/RIUP23/3991/BALAJI CONSTRUCTIO/UBIN0572632 ₹ 1,98,000.00
58486 |  |  | GST Release Note |  | 11 | 286611 | [10 empty] | 286611 |  |  | 500000 | 16-07-2024 NEFT/AXISP00519021668/RIUP24/0953/BALAJI CONSTRUCTIO/UBIN0572632 500000.00
58486 | randawali , jhabarpur,harinagar | pipeline work | Randawali , Jhabarpur,Harinagar Village Pipeline work | 2024-06-11 | 1 | 924297 | 0 | 924297 | 166373 | 1090670 | 9242.97 | 46214.85 | 92429.7 | 92429.7 | 166373 | 4184 | 679796 |  |  | 500000 | 12-03-2024 NEFT/AXISP00480051200/RIUP23/4787/BALAJI CONSTRUCTIO/UBIN0572632 500000.00
58486 |  |  | GST Release Note |  | 1 | 166373 | [10 empty] | 166373 |  |  | 365596 | 24-04-2024 NEFT/AXISP00493457035/RIUP24/0271/BALAJI CONSTRUCTIO/UBIN0572632 365596.00
58486 | randawali , jhabarpur,harinagar | pipeline work | Randawali , Jhabarpur,Harinagar Village Pipeline work | 2024-10-28 | 2 | 587193 | 52500 | 534693 | 96245 | 630938 | 5346.93 | 26734.65 | 26734.65 | 53469.3 | 96245 |  | 422407 |  |  | 179795 | 03-08-2024 NEFT/AXISP00524511286/RIUP24/1356/BALAJI CONSTRUCTIO/UBIN0572632 179795.00
58486 | [19 empty] | 286611 | 18-10-2024 NEFT/AXISP00555372145/RIUP24/2212/BALAJI CONSTRUCTIO/UBIN0572632 286611.00
58486 | [19 empty] | 300000 | 26-12-2024 Debit N/RIUP24/2402/BALAJI CONSTRU/INDBN26123786894 300000.0
59087 | ahrora | pipeline distribution network work | AHRORA village PIPELINE DISTRIBUTION NETWORK WORK AT AHRORA BLOCK | 2023-12-18 | 9 | 624115 | 4920 | 619195 | 111455 | 730650 | 6191.95 | 30959.75 | 61919.5 | 61919.5 | 111455 | 7507 | 450697 | 150000 | 1500 | 148500 | 01-09-2023 NEFT/AXISP00420941794/RIUP23/1818/BALAJI CONSTRUCTIO/UBIN0572632 ₹ 1,48,500.00
59087 |  |  | GST Release Note |  | 9 | 111455 | [10 empty] | 111455 | 302196 | 0 | 302196 | 09-01-2024 NEFT/AXISP00460826663/RIUP23/4009/BALAJI CONSTRUCTIO/UBIN0572632 302196.00
59087 | [19 empty] | 111455 | 30-03-2024 NEFT/AXISP00486493283/RIUP23/4838/BALAJI CONSTRUCTIO/UBIN0572632 111455.00
51700 | raee | development of tubewell work | Raee Village Development of tubewell work | 2022-08-04 | 2 | 50375 | 0 | 50375 | 0 | 0 | 1007.5 | 9067.5 | 0 | 0 | 0 |  | 49368
51700 |  |  | GST Release Note |  | 2 | 9067 | [10 empty] | 9067
51700 | meghakheri | development of tubewell work | Meghakheri Village Development of tubewell work | 2022-08-04 | 3 | 50375 | 0 | 50375 | 0 | 0 | 1007.5 | 9067.5 | 0 | 0 | 0 |  | 49368
51700 |  |  | GST Release Note |  | 3 | 9067 | [10 empty] | 9067
51700 | parai | development of tubewell work | Parai Village Development of tubewell work | 2022-08-04 | 4 | 50375 | 0 | 50375 | 0 | 0 | 1007.5 | 9067.5 | 0 | 0 | 0 |  | 49368
51700 |  |  | GST Release Note |  | 4 | 9067 | [10 empty] | 9067
51700 | datiyana | development of tubewell work | Datiyana Village Development of tubewell work | 2022-08-04 | 5 | 50375 | 0 | 50375 | 0 | 0 | 1007.5 | 9067.5 | 0 | 0 | 0 |  | 49368
51700 |  |  | GST Release Note |  | 5 | 9067 | [10 empty] | 9067
51700 | bibipur | development of tubewell work | Bibipur Village Development of tubewell work | 2022-08-06 | 6 | 50375 | 0 | 50375 | 0 | 0 | 1007.5 | 9067.5 | 0 | 0 | 0 |  | 49368
51700 | badhai khurd | development of tubewell work | BADHAI KHURD Village Development of tubewell work | 2022-08-06 | 7 | 50375 | 0 | 50375 | 0 | 0 | 1007.5 | 9067.5 | 0 | 0 | 0 |  | 49368
51700 | pachenda kalan | development of tubewell work | PACHENDA KALAN Village Development of tubewell work | 2022-08-06 | 8 | 50375 | 0 | 50375 | 0 | 0 | 1007.5 | 9067.5 | 0 | 0 | 0 |  | 49368
51700 | pachenda khurd | development of tubewell work | PACHENDA KHURD Village Development of tubewell work | 2022-08-06 | 9 | 50375 | 0 | 50375 | 0 | 0 | 1007.5 | 9067.5 | 0 | 0 | 0 |  | 49368
51700 | manganpur | development of tubewell work | MANGANPUR Village Development of tubewell work | 2022-10-28 | 17 | 50375 | 0 | 50375 | 0 | 0 | 1007.5 | 9067.5 | 0 | 0 | 0 |  | 49368
51700 | sandhiwali | development of tubewell work | SANDHIWALI Village Development of tubewell work | 2022-10-28 | 18 | 50375 | 0 | 50375 | 0 | 0 | 1007.5 | 9067.5 | 0 | 0 | 0 |  | 49368
51700 | badhkali | development of tubewell work | BADHKALI Village Development of tubewell work | 2022-10-28 | 19 | 50375 | 0 | 50375 | 0 | 0 | 1007.5 | 9067.5 | 0 | 0 | 0 |  | 49368
51700 | nirdhana | development of tubewell work | NIRDHANA Village Development of tubewell work | 2022-10-28 | 20 | 50375 | 0 | 50375 | 0 | 0 | 1007.5 | 9067.5 | 0 | 0 | 0 |  | 49368
51700 | bahpur | compressor work | Bahpur Village Compressor work | 2022-11-10 | 21 | 50375 | 0 | 50375 | 0 | 0 | 1007.5 | 9067.5 | 0 | 0 | 0 |  | 49368
51700 | sadpur | compressor work | Sadpur Village Compressor work | 2022-11-10 | 22 | 50375 | 0 | 50375 | 0 | 0 | 1007.5 | 9067.5 | 0 | 0 | 0 |  | 49368
51700 | nirgajni | compressor work | Nirgajni Village Compressor work | 2022-11-10 | 23 | 50375 | 0 | 50375 | 0 | 0 | 1007.5 | 9067.5 | 0 | 0 | 0 |  | 49368
51700 | mohiddinpur | compressor work | MOHIDDINPUR Village Compressor work | 2022-12-26 | 26 | 50375 |  | 50375 | 0 | 0 | 1007.5 | 9067.5 | 0 | 0 | 0 |  | 49368
51700 | athai | compressor work | ATHAI Village Compressor work | 2022-12-26 | 27 | 50375 |  | 50375 | 0 | 0 | 1007.5 | 9067.5 | 0 | 0 | 0 |  | 49368
51700 | jaitpur | compressor work | JAITPUR Village Compressor work | 2022-12-26 | 28 | 50375 |  | 50375 | 0 | 0 | 1007.5 | 9067.5 | 0 | 0 | 0 |  | 49368
51700 | abdulpur | compressor work | ABDULPUR Village Compressor work | 2022-12-26 | 29 | 50375 |  | 50375 | 0 | 0 | 1007.5 | 9067.5 | 0 | 0 | 0 |  | 49368
51700 | buwarakalan | compressor work | BUWARAKALAN Village Compressor work | 2022-12-26 | 30 | 50375 |  | 50375 | 0 | 0 | 1007.5 | 9067.5 | 0 | 0 | 0 |  | 49368
51700 | rampur | compressor work | RAMPUR Village Compressor work | 2022-12-26 | 31 | 50375 |  | 50375 | 0 | 0 | 1007.5 | 9067.5 | 0 | 0 | 0 |  | 49368
51700 | mubarikpur | compressor work | MUBARIKPUR Village Compressor work | 2023-01-28 | 36 | 50375 |  | 50375 | 0 | 0 | 1007.5 | 9067.5 | 0 | 0 | 0 |  | 49368
51700 | gujjarhedi | compressor work | GUJJARHEDI Village Compressor work | 2023-01-28 | 38 | 50375 |  | 50375 | 0 | 0 | 1007.5 | 9067.5 | 0 | 0 | 0 |  | 49368
51700 | kailanpur | compressor work | KAILANPUR Village Compressor work | 2023-01-28 | 39 | 50375 |  | 50375 | 0 | 0 | 1007.5 | 9067.5 | 0 | 0 | 0 |  | 49368
51700 | palda | compressor work | PALDA Village Compressor work | 2023-01-28 | 37 | 50375 |  | 50375 | 0 | 0 | 1007.5 | 9067.5 | 0 | 0 | 0 |  | 49368
51700 | malpura | compressor work | MALPURA Village Compressor work | 2023-03-15 | 45 | 50375 |  | 50375 | 0 | 0 | 1007.5 | 9067.5 | 0 | 0 | 0 |  | 49368
51700 | wajidpur kowali / chihamau | compressor work | WAJIDPUR KOWALI / CHIHAMAU Village Compressor work | 2023-03-15 | 46 | 50375 |  | 50375 | 0 | 0 | 1007.5 | 9067.5 | 0 | 0 | 0 |  | 49368
51700 | chihamau | compressor work | CHIHAMAU Village Compressor work | 2023-03-20 | 47 | 50375 |  | 50375 | 0 | 0 | 1007.5 | 9067.5 | 0 | 0 | 0 |  | 49368
51700 | dulhera | compressor work | DULHERA Village Compressor work | 2023-03-20 | 48 | 50375 |  | 50375 | 0 | 0 | 1007.5 | 9067.5 | 0 | 0 | 0 |  | 49368
51700 | shahbzpur tigai | compressor work | SHAHBZPUR TIGAI Village Compressor work | 2023-03-20 | 49 | 50375 |  | 50375 | 0 | 0 | 1007.5 | 9067.5 | 0 | 0 | 0 |  | 49368
51700 | shakarpur | compressor work | SHAKARPUR Village Compressor work | 2023-03-20 | 50 | 50375 |  | 50375 | 0 | 0 | 1007.5 | 9067.5 | 0 | 0 | 0 |  | 49368
51700 | sardhan | compressor work | SARDHAN Village Compressor work | 2023-04-10 | 1 | 50375 |  | 50375 | 0 | 0 | 1007.5 | 9067.5 | 0 | 0 | 0 |  | 49368
51700 | morkukka | compressor work | MORKUKKA Village Compressor work | 2023-10-09 | 16 | 50375 |  | 50375 | 0 | 0 | 1007.5 | 9067.5 | 0 | 0 | 0 |  | 49368
TOTAL | [5 empty] | 12013381.4 |  |  |  |  | 117629.24 | 734077.69 | 595669.14 |  |  | 166237 | 9281575.56 |  |  | 6816117
Contractor Name | Balaji construction
Date | Friday, 2025-05-16
Description | Amount
Advance/Surplus | 2465458.5599999987
Total Hold Amount | 166237
Amount With TDS | 117629.23999999998